## Sheet1
Task Group/Task | Task Assigned To | Task Completion Date | Week 6 2/13 | Week 6 2/15 | Week 7 2/18 | Week 7 2/22 | Week 8 2/25 | Week 8 3/1 | Week 9 3/4 | Week 9 3/8 | Week10 3/11
Documentation
Initial Software Requirements Specification | LH, ZB, LW | 2019-02-21
Initial Software Design Specification | CC, BY | 2019-02-21
Initial Project Plan ZB | ZB | 2019-02-21
Initial User Documentation | LH, LW | 2019-02-21
Initial Developer Documentation ZB | ZB | 2019-02-21
Tutorial Documentation | LW | 2019-03-12
Final Project Plan ZB | ZB | 2019-03-12
Final User Documentation | LW | 2019-03-12
Final Developer Documentation ZB | ZB | 2019-03-12
Final Software Requirements Specification | LH, LW | 2019-03-12
Final Software Design Specification | CC, BY | 2019-03-12
Prototypes
Prototype 1: Basic Backend Communication | ZB | 2019-02-15
Prototype 2: Basic 3D Model | ZB | 2019-02-22
Prototype 3: Basic 3D World | ZB | To Be Completed
Prototype 4: Basic 3d World with entities | ZB | To Be Completed
IO System
Vertex (Object) File Reading | LH | 2019-03-04
Image File Reading | LW, BY | 2019-03-08
Sound File Reading | BY | 2019-03-08
Shader File Reading | ZB | 2019-03-09
Testing
Prototype 1 Testing | ZB | 2019-02-22
Prototype 2 Testing | ZB, CC | 2019-03-04
Integration Testing | CC, ZB, LH | 2019-03-12
Prototype 3 Testing | ZB, CC, LH, LW | To Be Completed
Prototype 4 Testing | ZB, CC, LH, LW | To Be Completed
System Components
Setting up back end system | ZB | 2019-02-15
Real 3D rendering | ZB | 2019-02-20
Event Handling | CC | 2019-03-10
Object Creation | ZB, CC | 2019-03-04
Shader creation | ZB | 2019-03-01
Threading Complete | ZB, CC | 2019-03-09
File Reading/Parsing | BY, LH, LW | 2019-03-06
Collision Detection | CC, ZB | To Be Completed
Basic Artificial Intelligence | CC, ZB | To Be Completed
Team Members: | Last Updated By: | Linshu Huang
Chase Craig (CC), Linshu Huang (LH), Benjamin Yin (BY), Zach Bower (ZB), Luyao Wang (LW) | Last Updated On: | 2019-03-12
Note:
Due to the heavy snow and some members lost the power, internet access, and landlines, along with impassible roads preventing escaping into town. Therefore, the whole week 8 has almost no progress and the plans got delayed.
Color Indication
Different color indicate different type of the task, the lighter color for each section indicate the plan that was scheduled but actually not been implemented.